Eurogeographics

Quality Knowledge Exchange Network

Long Term Plan

Long Term Plan - planned activities

| History | File name: Long_Term_Plan_2009_1.0.doc |  |  |
| --- | --- | --- | --- |
| Version | Author | Date | Comments |
| 0.1 | CW | 1st April 2007 | First draft of EGQ’s Long Term Plan |
| 0.2 | CW | 21st June 2007 | Comments from CC meeting |
| 1.0 | AJ | 18th Feb 2008 | CC meeting |
| 1.1 | CA | 9th Sept 2008 | CC meeting – updated working groups and mapped objectives with EG strategic goals |
| 2.0 | CA | 11th Sept 2009 | CC meeting |
| 3.0 | JH | 27th Sept 2010 | CC meeting |
| 3.1 | JH | 29th Nov 2010 | Comments following CC review |
| 4.0 | JH | 16th Sept 2011 | CC Meeting |
| 5.0 | JH | 1st Oct 2012 | CC Meeting |
| 6.0 | JH | 18th Sept 2013 | CC Meeting |
| 7.0 | JH | 2nd July 2014 | CC Meeting |

##### Content

1. Purpose of this document	2

2. General information	3

3. Planned activities	3

# 1. Purpose of this document

- The long term plan will

- be an input to the yearly work plan

- clarify the objective for each action

- clarify responsibility for each action

- give a simple overview of all activities within the expert group of quality

- make it easier to change the plan when there is conflict in time etc.

The long term plan will be updated each year by the Co-ordinating committee (CC)

# 2. General information

The long term plan supports the strategic objectives of EuroGeographics namely

2.2 Develop the network of members

and

2.5 Grow our network of members

Topical issues are discussed and selected at the CC meetings for active discussion and breakout sessions at the next plenary meeting.

# 3. Planned activities

| Objective (members) | Action (group) | Responsibility | Deadline | Comments |
| --- | --- | --- | --- | --- |
| Support communication and the exchange of experience among the members and wider GI community | Update the Terminology glossary | Ourania | Continuously | Twice a year before plenary send a reminder to members |
|  | Maintain Q-KEN website | Chair | Continuously |  |
|  | Maintain Q-KEN forum via Basecamp for member discussion and inform of latest news and technical developments | All | Continuously |  |
|  | Run Webinars on topics of interest to the Q-KEN. | CC | Continuously | At least once but preferably twice a year. Planned at CC meetings. |
|  | Run a feedback questionnaire every 18 months to ensure that the activities of the Q-KEN are meeting the needs of the members | Celia | Every 18 months Next Spring 2016 |  |
|  | Grow our network of members to enable greater sharing and understanding of information | CC | Continuously | Jonathan to email all permanent correspondents |
| Take part in research activities to help the work in Q-KEN to go forward | Encourage academia and other organisations involved in quality to participate in the activities of the Q-KEN | CC | Continuously | Encourage and engage with groups like EuroSDR. |
|  | Run international workshop on Data Quality | CC | 2017/8 | Look to coincide with end of ELF |
| Keep up with the development of quality tools | Present news at plenary meeting | Members | Continuously |  |
|  | Identify other suppliers of Quality Control software through web searches, use of ESDIN and EuroSDR contacts, EuroGeographics website (posting news items etc), Q-KEN | CC | Continuously |  |
| Encourage that Quality standards are implemented in NMCAs | Follow-up how NMCAs have implemented the ISO standards | Gunhild | Periodically Next review by Spring 2016 |  |
|  | Follow the development of the ISO standards | Gunhild | Continuous |  |
|  | Review the ISO 19100 guidelines following the introduction of ISO19157 / 8 | CC | Start 2013 | Currently underway |
| Provide members with common quality evaluation procedures which can be applied to the European reference data | Propose standard for quality evaluation procedures | Vacant | Main work in 2015 / 2016 | ELF is delivering this |