## Sheet1
Q-KEN Action Log
ID | Meeting | Action / Results | Assigned To | Due Date | Date Closed
1 | Warsaw 2011 | CC to investigate whether the ISO 19100 implementation guidelines should be revisited in the light of ISO19157 - yes when guildlines are published | CC | 2012-10-01 | 2012-10-01
2 | Warsaw 2011 | Website document register. This is now ready to take forward. Action closed as Claude no longer available to take forward | Claude | Autumn 2012 | 2013-04-17
3 | Warsaw 2011 | Presentation on the Total revision of the Quality Management system in France (Need to check to see if this is still relevent) Action closed as Claude no longer available | CC / Claude | Autumn 2012 | 2013-04-17
4 | Warsaw 2011 | Presentation on the Nordic group for quality issues related to cadastral from Norway | Magni | Autumn 2012 | Issue closed
5 | Warsaw 2011 | Ourania to remove the unused fields from the terminology document | Ourania | Autumn 2012 | 2012-11-29
6 | Warsaw 2011 | Gunhild to produce the final report on the ISO questionnaire and to send it out. Complete 15/05 | Gunhild | Autumn 2012 | 2013-05-15
7 | Warsaw 2011 | Jonathan to pass the final definition of th quality model to Ourania for inclusion in the terminology document | Jonathan | Autumn 2012 | 2012-07-02
8 | Reykjavik 2012 | Carol to organise a webinar after the CC but before the plenary to review these actions | Carol | 2012-10-01 | 2012-11-05
9 | Reykjavik 2012 | Presentation on the Methodology handbooks on data quality | Tomas | Autumn 2012 | 2012-11-29
10 | Reykjavik 2012 | Presentation on the Use of Confluence software in ICC Spain. On agenda for Autumn plenary as joined with Qualty Management topic. | Jordi | Autumn 2013 | 2013-09-17
11 | Reykjavik 2012 | Anna to let Carol know if there will be a presentation from Iceland at the next plenary. | Anna | 2012-10-01 | 2012-11-05
12 | Reykjavik 2012 | Carol to finalise dates for webinars as follows: Inspire Data Specification on elevation from ICC Spain Data quality on land cover in Inspire Hungary Sampling techniques for geographic database IGN – Spain (spring 2013 plenary?) Experience from quality tests in the project Geotest – Sweden Sampling techniques was a request for information not a presentation. Action closed | Carol | Spring 2014 | 2013-03-05
13 | Reykjavik 2012 | Georg to contact Carol with a preferred date for a webinar on Workflows in Cadastre from Austria. (Now a presentation in Vienna) | Georg | 2012-09-01 | 2013-04-17
14 | Reykjavik 2012 | Carol to release an updated Quality Management Questionnaire | Carol | Autumn 2012 | 2012-11-02
15 | Reykjavik 2012 | CC to look at the possibility of creating another questionnaire around data quality | CC | 2013-02-01 | 2013-05-15
16 | Reykjavik 2012 | Everyone to review and pass comments on the EuroSDR archiving paper to Jonathan by 30.06.12 | All | 2012-06-30 | 2012-06-30
17 | Reykjavik 2012 | Carol to send out the ERM audit questionnaire (closed as too late) | Carol | 2012-06-20 | 2012-11-29
18 | Reykjavik 2012 | Georg to confirm the dates of the Vienna plenary in Spring 2013 to Carol. | Georg | 2012-10-01 | 2012-11-01
19 | Reykjavik 2012 | All to consider whether they could host a plenary meeting in Autumn 2013 | All | Autumn 2012 | 2012-11-29
20 | Reykjavik 2012 | Antti to place the details on how to unblock “Go to meeting” on basecamp. | Antti | 2012-06-20 | 2012-10-01
21 | Reykjavik 2012 | Christina to pass on the results of the INSPIRE data quality paper review. | Christina | 2012-06-30 | 2012-10-01
22 | Reykjavik 2012 | Jonathan / Ioannis to promote the use of the ESDIN quality model via Eurogeographics newsletter | Jonathan / Ioannis | 2012-06-21 | 2012-10-01
23 | Reykjavik 2012 | CC to consider the following as potential topics for a future plenary Developing comprehensive data quality management strategies for NMCAs (spring 2013) - Consider once ISO Handbook has been updated as this is part of it. This could in part be covered by the work with EuroSDR - 13/04/16 Procedures of choosing conformance levels for datasets which already exist (Autumn following results from DQ questionnaire) See item 63 Aggregation of data quality results for different datasets Done | CC | Spring 2016
24 | Reykjavik 2012 | Carol to look at the possibility of having webinar on ISO 27001 from Iceland and France Request to go to Registers of Iceland not the Icelandic Land Survey. France webinar unlikely to happen until Claude is replaced. Agreed CC in Brussels that this unlikely to happen now - Issue closed | Celia | Autumn 2013 | 2013-09-17
25 | Malta 2012 | Update ISO guildlines when ISO 19157 & 19158 are published -- ? Now in hand 17/09/2013 | CC | Autumn 2013 | 2013-10-22
26 | Zagreb 2012 | Specific topics from Czech Republic Methodology handbooks should be presented and discussed at Q-KEN. CC to take forward (This may not take place as contact has been lost with Tomas). Carol to try and find a new member from the Czech Republic to deliver this. Accepted that this is unlikely to happen. Issue closed | Carol | Spring 2014 | 2014-03-05
27 | Zagreb 2012 | Pre-plenary webinars to be agreed at the same time as the plenary date. CC to note | CC | Spring 2013 | 2013-04-17
28 | Zagreb 2012 | Pre-plenary webinars should be recorded. Carol to action | Carol | 2013-04-17 | 2013-04-17
29 | Zagreb 2012 | Next questionnaire should include a question about the pre-plenary | Celia | Spring 2013 | 2013-04-17
30 | Zagreb 2012 | Topics selected for next plenary in Vienna 15 - 17 May 2013 - Software checking of the quality of cadastral data - Tamas - Webmap service - Arvids - Public procurement of Quality Control - Marcin General software for quality control - ICC Spain and QMS in France (if still suitable) may be options for presentations as well. | CC | Spring 2013 | 2013-05-15
31 | Zagreb 2012 | Jonathan to contact IGN Spain to find out how "Process monitoring by automatically recording each of the actions or tasks performed by operators to facilitate process monitoring and optimization" is done and pass on the news via basecamp if relevent to the group. Closed - not relevant to the group | Jonathan | 2012-12-31 | 2013-04-17
32 | Zagreb 2012 | Carol to promote the Q-KEN Terminology document through the Eurogeographics newsletter To be replaced with a longer piece about the Q-Ken. To be republished after the Spring plenary. Action taken but not published yet 2/7/14. Close once released. Released in July | Carol | 2014-06-30 | 2014-09-09
33 | Zagreb 2012 | Questionaire on Data Quality Ken will combine the results from the two groups and form a questionnaire. This will be sent to the CC for review and publication. | Ken | 2013-01-01 | 2013-04-17
34 | Zagreb 2012 | Questionnaire on Data Quality CC to publish the questionnaire on Survey Monkey and send it to all Eurogeographics members. | CC | 2013-02-01 | 2013-05-15
35 | Zagreb 2012 | CC will discuss if Q-KEN should take two of the questions on Base Camp forward as specific topics at plenary/webinar - question about sampling (related to Anttis answer on BaseCamp) CC agreed 17/09/13 that this bit will not be taken forward any further - question about how to describe quality in customers way “How easy is it to understand data quality information from a customer perspective”. This is part of the quality questionnaire work now under way. Issue closed 17/09/13 | CC | Spring 2013 | 2013-09-17
36 | Zagreb 2012 | Jonathan will inform the members on Base Camp to look at the definition of certification and accreditation at Q-KEN web (Terminology) | Jonathan | 2012-11-30 | 2012-11-30
37 | Zagreb 2012 | CC to decide if Antti will still be the link with Inspire KEN and therefore responsible for that action in the Long term plan. Agreed by CC that Christina will be the link between the two groups | CC | Spring 2013 | 2013-04-17
38 | Zagreb 2012 | Future Webinars - CC to arrange Metadata presentation in terms of data quality on Czech Geoportal National or COSMC metadata profile, Czech Republic Maintaining quality in a seamless environment (OS, GB) - Given at Plenary in Budapest Automatic quality test (Slovenia) Closed 21/10/13 | CC | Winter 2013/4 | 2013-10-21
39 | Zagreb 2012 | Handbook 19131 (Gunhild, Sweden) This should be presented at a plenary – together with a presentation from Finland who have something similar. On Spring agenda | CC | Spring 2013 | 2013-04-17
40 | Zagreb 2012 | Thoughts from discussions about aggregated quality should be presented and discussed at next plenary in Vienna. Agreed at CC 17/09/13 that this wouldn't be progressed at this moment in time but that we would review the use of ADQ results in a years time. In particular we will look to see what response Spain and Latvia have received from their use of ADQ and whether they are able to present on this reaction. Jonathan will get in touch with Ana and Arvids regarding progress on this. Done but little response. To be taken forward with EuroSDR work? 13/04/16 | CC | 2014-09-30
41 | Zagreb 2012 | Tamas to let Carol know at the beginning of 2013 whether Budapest could be considered as a location for the Autumn 2013 plenary. Yes agreed 17/18 October | Tamas | 2013-01-01 | 2013-04-17
42 | Zagreb 2012 | Date for the next pre-plenary webinar agreed as 17/04/13. Carol to arrange. Agreed but then postponed by a week due to HO activity | Carol | 2013-01-01 | 2013-04-17
43 | Vienna 2013 | Presentations for the next plenary were agreed as follows · Data Quality Management Framework in GIGiK – Poland - Now Spring 2014 · New tool for recording errors detected by external users in a new database – IGN Spain · Development of a corporate web platform to present ISO 9001 – ICC Spain Postponed · QMS documentation using Confluence software – ICC Spain - Webinar at plenary · Establishment of data control checks between KFS and EGA – Austria - Cancelled as not of interest to the group · Validation routines in a seamless environment - OSGB | All | Spring 2014 | 2014-05-09
44 | Vienna 2013 | Carol to collate the results of the group work on crowdsourced and VGI data and make these available to everyone. Now completed 07/10/13 | Carol | 2013-05-31 | 2013-10-07
45 | Vienna 2013 | Carol to pass the results of the group work on crowdsourced and VGI data to Head Office for inclusion in the UN discussion. Deadline missed and now too late. Issue closed 17/09/2013 | Carol | 2013-05-31 | 2013-09-17
46 | Vienna 2013 | There should be a further discussion at the next plenary to see what has happened in the NMCAs in the last six months on crowdsourced and VGI data. Closed 21/10/13 | CC | Autumn 2013 | 2013-10-21
47 | Vienna 2013 | Everyone to discuss what the situation is with crowdsourcing and VGI data within their own organisations. On Agenda for Autumn plenary | All | Autumn 2013 | 2013-09-17
48 | Vienna 2013 | Jonathan to circulate the EuroSDR crowdsourcing document on basecamp | Jonathan | 2013-05-31 | 2013-09-17
49 | Vienna 2013 | Carol to chase those countries that only partially answered or didn’t answer the quality management questionnaire at all and then re-assess the answers. Completed 07/10/13 | Carol | 2013-08-31 | 2013-10-07
50 | Vienna 2013 | CC will review the results of the quality management questionnaire at the next CC meeting | CC | Autumn 2013 | 2013-10-07
51 | Vienna 2013 | Gunhild to put a copy of Swedish ISO 19131 handbook on basecamp. Made available to CC but not on basecamp yet. CC looking at whether this will be useful to translate. | Gunhild | 2013-05-31 | 2013-10-07
52 | Vienna 2013 | Saulius to see if it is possible for EGHO to have the Swedish ISO19131 handbook translated into English. Agreed with HO that Qken funds could be used for this. Agreed that this might be possible but Jonathan to look at Google translate to see what results could be achieved first. Placed on basecamp 5/3/14 - awaiting feedback - decision to be made at Malmo meeting Agreed that this was worthwhile translating this. Gunhild will try and get a price from Lantmateriat for doing this. 110 Swedish Kr per word. Christina is looking to see if this could be done cheaper in Sweden. Document should be available in English in November 2015. Gunhild to report on progress | Gunhild | Autumn 2015 | 2016-05-20
53 | Vienna 2013 | Tamás to confirm that the next plenary will be in Budapest on 21st – 22nd October | Tamás | 2013-05-31 | 2013-09-17
54 | Vienna 2013 | Jonathan to initiate the discussion via Basecamp on the ISO handbook | Jonathan | 2013-05-31 | 2013-10-22
55 | Vienna 2013 | Jonathan to seek further responses to the QKEN members on the Data Quality Questionnaire | Jonathan | 2013-08-31 | 2013-09-17
56 | Vienna 2013 | The data quality questionnaire will also be extended to all EGG members – Deadline for responses 31/08/13. Completed | Carol | 2013-08-31 | 2013-10-21
57 | Budapest 2013 | Identify a contact from each country to represent quality. Carol has written to each Permanent Correspondent but has received little response. She will chase this up at the ExtraOrdinary General Meeting next week. If this fails the Saulius will raise this at the AGM in September and ask each CEO to nominate a member. Jonathan will pick this up at the ExGA in Leuven when the Permanent Correspondents will be present. | Jonathan | Spring 2016
58 | Budapest 2013 | Identify a way to record some of the presentations so that those who cannot attend can get some benefit from them. Recordings made at Malmo Spring 2014. Awaiting feedback to see if this was successful Virginie will chase progress on this Some of these have been uploaded but not all. CC to review the idea, progress and feedback. Action is ongoing. Review after Athens plenary when some of the recordings have been made. | CC | 2016-07-31
59 | Budapest 2013 | Could Matt Beare (co- chair OGC Data Quality Group) become a member of the group? Saulius will get back to CC on this 06/03/14 Dave Lovell stated that the answer to this is no, but there is no reason why the Chair couldn't invite him to every meeting. | CC | 2015-07-01 | 2015-09-10
60 | Budapest 2013 | Can Q-Ken help with the introduction of quality validation to national processes? In particular to the EuroGeographics projects. CC to consider. This will be taken to the producers meeting in April. This may fall out of ELF. Answer no. | CC | Spring 2015 | 2015-09-10
61 | Budapest 2013 | Carol to re-circulate the Quality Management Questionnaire and results together with the output from the working groups. The group will be asked what we should do next with the questionnaire. Carol to take this forward as part of her Masters. Action closed | Carol | 2013-11-30 | 2014-03-05
62 | Budapest 2013 | Presentations for the next plenary are: Acceptance sampling inspection from Greece - On spring 2014 agenda Generic model for the work on data quality from Denmark - Possibly on agenda Review of the Geodata Standard with ISO 19157 from Norway - For Autumn 2014 Neither likely to happen. Issue closed 09/09/14 | CC | Spring 2014 | 2014-09-09
63 | Budapest 2013 | CC to look at the issue of how NMCAs define quality requirements – do we wish to continue with this idea? - On agenda Spring 2014. This was discussed and best practice is being identified by Jordi, Thierry and Karin Jordi and Ana will complete this work by the end of November. Still outstanding. Jordi to forward the document in the next week Carol will then carry out an English check and publish the document on the website. On the members only side of the website | Jordi, Thierry, Karin Carol | 17/09/2015 | 2016-04-13
64 | Budapest 2013 | Saulius to investigate whether it was possible to have an email address that would automatically create a new thread in Basecamp. Done 23/10/13 | Saulius | 2013-11-30 | 2013-10-23
65 | Budapest 2013 | CC to look at whether it is possible to define “Authoritative” - In hand | CC | Spring 2014 | 2014-05-09
66 | Budapest 2013 | Jonathan to ask Ourania (Done 23/10/13) to add the definitions of VGI and Crowdsourcing to the terminology document along with any other new terms from ISO 19157. | Ourania | Spring 2014 | 2014-05-09
67 | Budapest 2013 | Carol to place the latest version of the terminology document on the website | Carol | 2013-11-30 | 2013-11-30
68 | Budapest 2013 | ISO Guidelines working group to read the document before the webinar. | Ken / Marcin / Gunhild / Zenek / Jonathan | 2013-11-28 | 2013-11-28
69 | Budapest 2013 | Jonathan to distribute the ISO guidelines document to the group asap | Jonathan | 2013-10-25 | 2013-10-23
70 | Budapest 2013 | CC to publish the Quality Questionnaire report as is and send a copy direct to the quality contact in each organisation when they are identified | CC | Spring 2014 | 2014-05-09
71 | Budapest 2013 | Carol to mention the results of the Quality Questionnaire report in the EuroGeographics newsletter piece after the plenary | Carol | 2013-10-31 | 2014-05-09
72 | Budapest 2013 | Carol to start a wishlist for webinars on basecamp. The first topic will be the ISO 8000 standard. | Carol | 2013-10-31 | 2014-03-05
73 | Malmo 2014 | The presentations at the next plenary will be. Lessons learnt from re-engineering – Ken The possibility of using Lidar for quick updating of building features – Carol Testing against own specification and displaying the results – Gunhild New quality tool – ProSuite - Alexander | Ken, Carol, Gunhild and Alexander | Autumn 2014 | 2014-09-17
74 | Malmo 2014 | Saulius will update the group on the outcome of next weeks ELF WP4 meeting via Basecamp. Still to be done | Saulius | 2014-10-01 | 2014-09-17
75 | Malmo 2014 | Christina, Ken, Saulius and Zenek will all look to see if they can make contact with their national statistics offices to look for a presentation on quality control within their remit. To be set up for 20th October. 2pm CET | Christina, Ken, Saulius and Zenek | 2014-10-20 | 2014-10-20
76 | Malmo 2014 | Antti will try and persuade his contact to give us a presentation on the updates to ISO9001:2015 Carol to contact Antti again. - Possible Nov webinar? | Antti | 2014-11-30 | 2014-11-30
77 | Malmo 2014 | Gunhild will see if her contact is willing to present on ISO8000. They are! Carol and Gunhild will arrange a date for this in November. Carol to look for dates in Feb and March and get back to Gunhild | Gunhild / Carol | 2015-01-31 | 2015-09-10
78 | Malmo 2014 | Jonathan will update the terminology document with the decisions made in the plenary and circulate the new issues via basecamp. Once agreed this will be passed back to Ourania. | Jonathan | 2014-06-30 | 2014-09-30
79 | Barcelona 2014 | Jonathan will take forward the completion of the ISO guidelines work with the rest of the group. This will utilise the following as case studies Revision of the Geodata standard – Norway Implementation of ISO 19157 for public procurement in Poland | Jonathan / ISO Group | Autumn 2015
80 | Barcelona 2014 | The topic for the next plenary in Malta will be Data Quality validation in ELF WP4 from IGN Spain. Ana / Celia to confirm that this is possible. Likely to be later meeting in Autumn 2015. | Ana / Celia | 2015-11-30 | 2015-10-16
81 | Barcelona 2014 | Jonathan will organise a webinar in early 2015 of the Introduction of ISO 9001 guidelines for terrain / obstacles database with presentations from Ireland and Latvia. Carol to talk to Angela in EuroControl before setting this up. Igita to feed back on possibility to Jonathan who will then arrange the date. Avoid Mondays and Fridays. Carol is setting up a doodle poll to set this up in June 16. | Carol Igita Jonathan | 2016-01-31
82 | Barcelona 2014 | Carol to chase for confirmation that the Autumn 2015 meeting will be in Athens. Athens will not take place in 2015 but may be 2016. | Carol | 2014-12-31 | 2015-01-22
83 | Barcelona 2014 | Ken will formulate the plan on how to take the “Lessons learned in Data Re-engineering” forward and decide what aspect we will look at and who will be involved. Ken is awaiting the outcome on next weeks work shop before deciding how to take this forward. (Jan 15) Following discussions within the QKen it was agreed that this couldn't be benchmarked but both Jonathan and Peter Hallahan offered themselves as experts who were quite willing to help others | Ken | Spring 2015 | 2015-10-16
84 | Barcelona 2014 | Feedback questionnaire. Action to all to complete this once the questionnaire is made available | All | 2014-11-30 | 2015-01-22
85 | Barcelona 2014 | Terminology. Jonathan will update the document and send it to Ourania. Carol will place this updated version on the website. Jan 2015 - Carol to place on website | Carol | 2015-01-31 | 2015-09-10
86 | Barcelona 2014 | Alexander and Igita will provide their email addresses to Saulius so that they get included on Basecamp | Alexander and Igita | 2014-09-30 | 2015-01-22
87 | Malta 2015 | The next plenary will be in Madrid in the Autumn. Ana will put forward dates to Carol. | Ana | 2015-03-31 | 2015-09-10
88 | Malta 2015 | Carol to supply links to the videos that are available on the website | Carol | 2015-03-31 | 2016-04-13
89 | Malta 2015 | Presentations at the next plenary in Madrid will be: Automated checks on topographic data – SwissTopo - Stefan Effectiveness of National Topographic Database – Finland - Juha Implementation of ISO19157 – HMLR GB - Gareth Hungarian building monitoring system – Hungary - Tamás. Jonathan to contact Tamas to see if he is likely to be at the next plenary session if not make this a webinar. Edition of data specs for the datasets of the Regional Cartographic Plan of Catalonia (PCC) Adaption to INSPIRE – Spain - Jordi | Stefan Juha Gareth Tamás Jordi | Spring Plenary 2016 | 2016-05-20
90 | Malta 2015 | SDMQ - Benchmarking of presentations – Can we do this? Carol to speak to Antti to get this underway asap. Issue closed | Carol | 2015-01-31 | 2015-09-10
91 | Malta 2015 | SDMQ - We need to re-do this in two years’ time although we should try and arrange it so that the meeting isn’t in the same year as the Synopsium on Spatial Data Quality. Future topics: VGI and how we are using it. What initiatives there are and how we can use them Lean principles – we’d like to know about this. | CC | 2015-12-31
92 | Malta 2015 | How QKEN can help ELF. CC to take this discussion forward - probably too late now | CC | 2015-08-30 | 2016-04-13
93 | Madrid 2015 | Presentations for the next plenary in Athens will be:- Quality control process for the updating of our roads and buildings (scale 1:10k) is set (Belgium) Work on social responsibility (France) New GIS environment for the production of the 5K Topo DB based on Geomedia, ID’s, lifecycle, customized tools for 3D (Catalonia) | Karin Thierry Joel | Spring 2016 | 2016-05-20
94 | Madrid 2015 | Consider Validation of the whole dataset as a subject for the coming plenary meeting | CC | Spring 2016 | 2016-05-20
95 | Madrid 2015 | All to provide feedback on the proposed standard UNE 148002 | All | Christmas 2015 | 2016-04-13
96 | Athens 2016 | Jonathan to raise the following question on Basecamp. Should we introduce extra terms on project management and total quality management, like ELF? | Jonathan | 2016-06-01
97 | Athens 2016 | Jonathan will compile a single side from the discussion on the work with EuroSDR and then distribute it early on Monday for review comments by the end of Tuesday. | Jonathan | 23rd May 2016
98 | Athens 2016 | Jonathan to out a question out on Basecamp to see who else is interested in presenting on the visual quality control via a webinar and for other topics as well. | Jonathan | 2016-06-01
99 | Athens 2016 | Gunhild will make the Quality Practitioner Document available on basecamp | Gunhild | 2016-06-01
100 | Athens 2016 | Presentations at the next plenary in France will be:- - Production and Quality control of ERM (Alexander) - Introduction of a quarantine step within the data capture workflow (GMS) (Ireland) + reasons why you would want a Quarantine step (Peter) - Designing a new visual methodology for quality control of the GRI of Transport Network in the production process (Ana) - Documentation system for data specifications (Sweden) - Visual inspection of orthoimagery (Greece) | Alexander Peter Ana Gunhild Ioannis | Autumn 2016